## Buda
Part Number	Name	qty	Unit	1430	Vendor	Vendor PN	Total	Order qty		PO	PO Date	Expected Date	Notes

PP-MP0052	2.0 Lower Plate	1	ea	1.20	Custom Laser		1430	1450	ea	PO04511	09/17/14	10/08/14	Quote requested 9/11	9/30/2014 Sent email to confirm delivery date. TS
PP-MP0023	1.1 Upper Plate	1	ea	1.20	Custom Laser		1430	1450	ea	PO04511	09/17/14	10/08/14	Quote requested 9/11	9/30/2014 Sent email to confirm delivery date. TS

EL-TH0001	100k Honeywell Axial Thermistor	1	ea	0.63	Digikey	480-3135-ND	1430	1450	ea	PO04558	09/19/14	09/30/14
EL-WR0104	24AWG Stranded – Orange, 1000ft	2600	mm	0.54	Digikey	C2015A-1000-ND	260000	0	Spools				Only for retail
EL-WR0112	24AWG Stranded – Red, 1000ft	2600	mm	0.54	Digikey	C2015R-1000-ND	260000	0	Spools				Only for retail
PC-RE0007	Heat Resistor, 4.7 Ohm	1	ea	0.41	Digikey	RWMB-4.7CT-ND	1430	1500	ea	PO04558	09/19/14	09/30/14
EL-MS0059	CONN TERM FEMALE 22-24AWG TIN	6	ea	0.33	Digikey	WM2510-ND	600	620	ea	PO04558	09/19/14	09/30/14	Only for retail
EL-MS0061	CONN HOUSING MALE 4POS .100	1	ea	0.24	Digikey	WM2535-ND	1430	1450	ea	PO04558	09/19/14	09/30/14
EL-MS0205	CONN TERM MALE 22-24AWG TIN	4	ea	0.22	Digikey	WM2517TR-ND	5720	0	ea	PO04558	09/19/14	09/30/14	Use reel ordered for Camellia
PC-CN0001	CONN HOUSING 2POS .100 W/LATCH	1	ea	0.25	Digikey	WM2900-ND	100	110	ea	PO04558	09/19/14	09/26/14	Only for retail
EL-MS0062	CONN HOUSING 4POS .100 W/LATCH	1	ea	0.41	Digikey	WM2902-ND	100	110	ea	PO04558	09/19/14	09/30/14	Only for retail

HD-TB0021	PTFE Tube for 3mm	1	ea	0.27	Eplastics/Ridout Plastics		1430	1450	ea	PO04605	09/29/14	10/24/14	We have enough in stock for 17 days of build, so we should be OK with the lead time.

PP-MP0042	2.0 heat sink washer	5	ea	0.69	EPOCS		7150	7170	ea	PO04484	09/15/14	10/06/14
PP-MP0017	1.1 Backup Plate	1	ea	1.90	EPOCS		1430	1450	ea	PO04484	09/15/14	10/06/14

PP-MP0050-4	Nozzle v2.0, 0.50mm	1	ea	5.95	MBK			255	ea	PO04480	09/15/14	10/05/14		Needs incoming inspection for cleaning
PP-MP0050-3	Nozzle v2.0, 0.35mm	1	ea	5.95	MBK			1290	ea	PO04480	09/15/14	10/05/14		Needs incoming inspection for cleaning
PP-MP0043	Heater Block v2.0	1	ea	4.80	MBK		1430	1440	ea	PO04480	09/15/14	10/05/14
PP-MP0051	2.0 PEEK isolator	1	ea	6.85	MBK		1430	1440	ea	PO04480	09/15/14	10/05/14
PP-MP0048	2.0 threaded extension	1	ea	3.85	MBK		1430	1440	ea	PO04480	09/15/14	10/05/14
PP-MP0046	Budaschnozzle 2.0 Mount Plate	1	ea	6.80	MBK		1430	1440	ea	PO04480	09/15/14	10/05/14

HD-TB0008	PTFE Insulation, 20 AWG, 1' Length	72	mm		McMaster	5335K13	102960	400	Feet	PO04613	09/29/14	10/01/14
HD-TB0010	PTFE Insulation, 13 AWG, 1' Length	36	mm		McMaster	5335K18	51480	200	Feet	PO04613	09/29/14	10/01/14
HD-TB0009	PTFE Insulation, 11 AWG, 1' Length	36	mm		McMaster	5335K19	51480	200	Feet	PO04613	09/29/14	10/01/14
EL-MS0012	Wire Ferrules 22-20 AWG, Packs of 100	2	ea	0.10	McMaster	9681K15	2860	30	pkg	PO04613	09/29/14	10/01/14
EL-MS0014	Noninsulated Wire Ferrule, 16 AWG, .28" Pin Length	2	ea	0.12	McMaster	9681K21	2860	30	pkg	PO04613	09/29/14	10/01/14
TL-CS0040	Extreme-Temperature Pipe Sealant & Threadlocker, 4 oz bottle, blue	0.5	g		McMaster	7604A55	715	5	4 oz bottle	PO04521	09/18/14	09/22/14
TL-CS0024	Commercial Grade Pipe Thread Sealant Tape 50'L X 1/4" W, .0028" Thk, 0.5 G/CC Specific Gravity	150	mm	0.01	Mcmaster	4591K11	214500	15	rolls	PO04613	09/29/14	10/01/14

EL-WR0041	Wire - Single Conductor 24AWG SOLID PTFE 100ft SPOOL ORANGE	360	mm	0.79	Mouser	602-2854/1-100-08	514800	18	Spools	PO04556	09/19/14	See Notes	10 spools landing by 9/26/2014 – Remaining 8 by 11/14/2014
EL-WR0040	Wire - Single Conductor 20AWG SOLID PTFE 100ft SPOOL RED	360	mm	1.10	Mouser	602-2856/1-100-03	514800	18	Spools	PO04556	09/19/14	See Notes	9 spools landing by 9/26/2014 – Remaining 9 by 11/14/2014

HD-WA0024	Low-Friction, PTFE Flat Washer, No. 12 screw size, .5" OD, .057"-.067" Thick	4	ea	0.09	Seastrom Mfg	5612-144-62	5720	5750	ea

SH-PA0018	Bubble 1/8RPB210P; 1/8"x6"X500'PERF@12	1	ea	0.08	Shippers Supply	B-1/8-6P12	100		Roll				need to check inventory

HD-BT0043	M3 x 35mm SHCS	3	ea	0.29	Mcmaster	91290a135	4290	4350	ea	PO04574	09/23/14	09/26/14
HD-WA0001	M3 Washer	3	ea	0.05	Timberline		4290	4350	ea	PO04552	09/19/14	09/30/14
HD-BT0031	M3 x 4mm set screw	1	ea	0.10	Mcmaster	92015A102	1430	1500	ea	PO04574	09/23/14	09/26/14

SH-PG0025	5 x 8” 2 Mil Reclosable Bags	1	ea	0.02	Uline	S-1295	100		Case				need to check inventory
SH-PG0022	4 x 3 x 3" Indestructo Mailers	1	ea	0.21	Uline	S-417	100		ea				need to check inventory

SH-MS0024	Shipping Label, 3.5x2.5 LulzBot Budaschnozzle 2.0, 0.5mm	1	ea	0.03	Light Speed		100	100
SH-MS0023	Shipping Label, 3.5x2.5 LulzBot Budaschnozzle 2.0, 0.35mm	1	ea	0.03	Light Speed		0						need to check inventory
	Case Box	0.0208333333333	ea	0.12			2.0833333333333						need to check inventory

	This order is made up of
	1030x for Ironwood
	100x 0.35 boxed for retail
	100x 0.35 for print heads
	200x 0.50 for print heads
	50x extra nozzles, 0.50
	50x extra nozzles, 0.35