## Sheet1
	EasyTAZ Mini – Product Development Cycle – v3.0_Draft
	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
Wdays to Launch	92					49					20				0
	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
	Design Validation – Functionally focused					Verification – Reliability focused – RBF					Qual – MFG/ Quality				Ramp			Sell, Sell, Sell!
	5-8 machines					15 machines					30-50 machines				120-140 machines			30-40/wk
	6/09					8/11					9/22				10-20			11-10
	Design Config LOCKED					Build DVT machines					Build SAT machines				Start production			Announce product
	auto bed leveling, hexagon nozzle					DVT Code release					SAT Code freeze
	PcD-Core/Baseboard, LCD					(except Video production)

			6/24
			LCD/T.Scr samples recv					8/18				9/15
				7/01					Order Daffodil				Order Production				10-17
				BB Design completed					long lead & low risk				long lead & low risk parts				Ship
						parts					Approved
					7/08		7/25		8/08			8/29			9/19
					Order DVT		3 Core/BB		DVT			Foam prototype			SAT
					frames		EVT testing		Entry			checkpoint			Entry
						Review					Review
	Items to Validate:					# of machine				Items to Verify:				# machine		To Verify:			Mach
	1)	Printability				5				1) Performance(speed,...)				15		Manufacturability			30
	2)	Repeatability				use above				2) Repeatability/Reliability				use above		Longterm Reliability			same
	3)	Userablity				use above				3) Userability				use above
	4)	Mechanical Spec				use above				4) Environmental				3
	5)	Electrical spec				use above				5) Op Shock/ Vibration				3
						6) Non-Opshock				use above
						7) EMC/FCC				3
	Type of Test					Type of Test				How long?		Type of Test
	1)	Can it print as well as Guava					1) Print-Visual/Time measure				24	hr	Long term reliability			72hr
	2)	Is bed leveling working					2) Short print/Cal, 24hr print				3	hr/ea	Assembly test run
	3)	Frame Stiffness					3) Hot, Hot/wet, Cold
	4)	Basic Electronics Function					4) Bump test
	5)					5) Drop test
						6) Near/far field test & FCC
	Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria					Test Accpt or P/F Criteria
	1)					1)					No Calibration drift, visual/
	2)					2)					Measurement, dimension
	3)					3)					Accuracy, consistency,
	4)					4)					visual printing quality
	Rules:	Design changes allowed - No architect-related changes					- Minor changes/improvements from RBF					- MFG/ “Ship” config hence NO change unless last minute discovery renders machine not shippable, require PAC approval
		After config “locked” date unless program risks such as					cycles allowed, no design -
		schedule, cost, … are studied & approved by the					config/architect- related changes
		Project Approval Committee (PAC-stakeholders)					unless approved by PAC
	PAC		Seth:
	Signed Off		Steven:
			Chris:
			Jeff:
	EasyTAZ Mini – Product Development Cycle_ Software & Firmware Functions & Features
	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
	92					49					20				0
	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
	Design Validation – Functionally focused					Verification – Reliability focused – RBF					Qual – MFG/ Quality				Ramp			Sell, Sell, Sell!
	5-8 machines					15 machines					30-50 machines				120-140 machines			30-40/wk
	6/09					8/11					9/22				10-20			11-10
	Design Config LOCKED					Build DVT machines					Build SAT machines				Start production			Announce product
	auto bed leveling, hexagon nozzle					DVT Code release					SAT Code release
	PcD-Core/Baseboard, LCD					(except Video production)

			6/24
			LCD/T.Scr samples recv					8/18				9/15
				7/01					Order Daffodil				Order Production				10-17
				BB Design completed					long lead & low risk				long lead & low risk parts				Ship
						parts					Approved
					7/08		7/25		8/08			8/29			9/19
					Order DVT		3 Core/BB		DVT			Foam prototype			SAT
					frames		EVT testing		Entry			checkpoint			Entry
						Review					Review

	Expected SW/FW Functions & Features

						- Working custom SD Image					-
	-					- Repo with packages for Slic3r, Octoprint, Custom Software					-
	-					- Ability to load files from USB drive					-
	-					- Ability to load files from USB drive					-
	-					- Connect/configure wifi					-
	-					- Control LED Strips via software					-
	-					- Web Daemon to interact with system calls					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-

	EasyTAZ Mini – Product Development Cycle_ ELECTRONICS CONFIGURATION
	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
	92					49					20				0
	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
	Design Validation – Functionally focused					Verification – Reliability focused – RBF					Qual – MFG/ Quality				Ramp			Sell, Sell, Sell!
	5-8 machines					15 machines					30-50 machines				120-140 machines			30-40/wk
	6/09					8/11					9/22				10-20			11-10
	Design Config LOCKED					Build DVT machines					Build SAT machines				Start production			Announce product
	auto bed leveling, hexagon nozzle					DVT Code release					SAT Code release
	PcD-Core/Baseboard, LCD					(except Video production)

			6/24
			LCD/T.Scr samples recv					8/18				9/15
				7/01					Order Daffodil				Order Production				10-17
				BB Design completed					long lead & low risk				long lead & low risk parts				Ship
						parts					Approved
					7/08		7/25		8/08			8/29			9/19
					Order DVT		3 Core/BB		DVT			Foam prototype			SAT
					frames		EVT testing		Entry			checkpoint			Entry
						Review					Review

	Expected Electronic Configuration

	Motion Controller			Rambo 1.3L					Mini- Rambo, rev?					Mini- Rambo, rev?
	Comm Controller:			Olimex					PC Druino: Core + Baseboard, rev 1.0					Core/ Baseboard, rev?
						-
	LCD:			Olimex					PC Druino Rev #?					-
	USB:					?					-
	WiFi:					Dongle					-

	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-
	-					-					-