## Sheet1
	EasyTAZ Mini – Product Development Cycle – v3.1_Draft					Lulzbot Mini – Product Development Cycle – v3.2
	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15
Wdays to Launch	92					49
	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-		EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia)					Production & Inventory Buildup / (Daffodil)		CYBER Monday	Production & Inventory Buildup / (Daffodil)
	Design Validation – Functionally focused					Finalize Final Design Config.					Reliability/Quality & Manufacturability focused					Ramp
	11-15 machines					25 machines		10-15 machines					25 machines					250 – 400 boxed machines
	6/09					8/11
	Design Config LOCKED					Build DVT machines		8/29					9/29
	auto bed leveling, hexagon nozzle					DVT Code release		Finalize designs & BOM					Build & Test QUAL machines
	PcD-Core/Baseboard, LCD
				9/02	(4 wks to 9/29)					10-13	(4 wks to 11/17)
			6/24					Order Camellia parts – nozzles, frames, P/S,					Order Production – short leads
			LCD/T.Scr samples recv					8/04		8/18
				7/01					3 Core/BB		Order Daffodil		9/02
				Machine for FOAM prototype				9/29
				Mach to verify Foam design
				9/12
				SW Pkg Selected
				BB Design completed					EVT testing		long lead & low risk
				parts			9/08	(10 wks to 11/17)					11-14
				7/08				8/08					Order Production long leads -			9/29				10/27		Ship
				drive rods, heaters, glass,			Camellia SW Release				Final SW		Approved
				P/S, bushings, fans, pwr switch
				Order DVT				DVT
				8/29				9/22
				Order MFG line 2				Line 2
				frames				Entry					Construction
				Review
	Items to Validate:					# of machine				Items to Verify:		Designs to Finalize					Items to Verify:			# mach		Duration
	1)	Printability				5				1) Performance(speed,...)		1) Nozzle – retention					* DVT
	2)	Repeatability				use above				2) Repeatability/Reliability		2) Mini Rambo – Pins in place of reset button					1) Performance(speed,...)
	3)	Userablity				use above				3) Userability		3) Z-Overrun Switch					2) Repeatability/Reliability
	4)	Mechanical Spec				use above				4) Environmental		- Reset RAMBO?					3) Userability
	5)	Electrical spec				use above				5) Op Shock/ Vibration		- Pins on RAMBO?					4) Environmental
				6) Non-Opshock		- Z-Lift?					5) Op Shock/ Vibration
				7) EMC/FCC		4) Bed Mounting – New corners?					6) Non-Opshock
	Type of Test					Type of Test		5) Glue – Best glue procedure					7) EMC/FCC
	1)	Can it print as well as Guava					1) Print-Visual/Time measure		6) Cables/Wires – Identify all components
	2)	Is bed leveling working					2) Short print/Cal, 24hr print		7) Thermal Cutoff – Firmware
	3)	Frame Stiffness					3) Hot, Hot/wet, Cold		8) Frame Design – final version, new left cover					* SAT
	4)	Basic Electronics Function					4) Bump test					1) Manufacturability			>25
	5)					5) Drop test					- Daffodil builds, pilot builds
				6) Near/far field test & FCC					2) Longterm Reliability
	Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria					- Cluster			>10		> 100 Hrs
	Rules:	Design changes allowed - No architect-related changes					- Minor changes/improvements from RBF					- MFG/ “Ship” config hence NO change unless last minute discovery renders machine not shippable, require PAC approval
		After config “locked” date unless program risks such as					cycles allowed, no design -
		schedule, cost, … are studied & approved by the					config/architect- related changes
		Project Approval Committee (PAC-stakeholders)					unless approved by PAC
	PAC		Seth:
	Signed Off		Steven:
			Chris:
			Jeff: